## Sheet1
S.No. | Package Name | Need Upgrade (Y/N/Revisit/Remove) | Upgrade to version (Version/Revisit/NA) | Priority (P0, P1, P3) | Evaluator | Status (Not Started, Ongoing, PR Raised, PR in Review, Done-Upgrade, Done-FixBuild, Done-OtherChanges, NA-Uptodate) | PR Link | Start Date | End Date | Last activity date | 3.0-dev Daily Build status (Y/N) | Build status date | Version in 2.0 | Version in 3.0 | Latest Version (Fedora Sources) | Fedora Sources Link | Latest Upstream Version | Upstream Sources Link | Remark / Plan for the package
1 | bolt | Y | 0.9.8 |  | Akarsh | Ongoing | [6 empty] | 0.9.2 | 0.9.2 | 0.9.8 | https://kojipkgs.fedoraproject.org//packages/bolt/0.9.8/3.fc41/src/bolt-0.9.8-3.fc41.src.rpm | 0.9.8 | https://gitlab.freedesktop.org/bolt/bolt
2 | boom-boot | Y | 1.6.5 |  | Akarsh | PR Raised | Upgrade: boom-boot to version 1.6.5 by AkarshHCL · Pull Request #10919 · microsoft/azurelinux | 2024-11-04 | 2024-11-04 | 2024-11-04 | Y | 2024-11-04 | 1.2 | 1.2 | 1.6.5 | https://kojipkgs.fedoraproject.org//packages/boom-boot/1.6.5/1.fc42/src/boom-boot-1.6.5-1.fc42.src.rpm | 1.6.5 | boom-boot/boom-boot.spec at main · snapshotmanager/boom-boot · GitHub
3 | booth | Y | 1.2 |  | Akarsh | Not Started | [6 empty] | 1 | 1 | 1.2 | https://kojipkgs.fedoraproject.org//packages/booth/1.2/2.fc41/aarch64/booth-1.2-2.fc41.aarch64.rpm | 1.2 | https://github.com/ClusterLabs/booth
4 | botan2 | Y | 2.19.5 |  | Akarsh | PR Raised | Upgrade:botan2 to version 2.19.5 by AkarshHCL · Pull Request #11051 · microsoft/azurelinux | 2024-11-05 | 2024-11-05 | 2024-11-05 | Y | 2024-11-05 | 2.14.0 | 2.14.0 | 2.19.5 | https://kojipkgs.fedoraproject.org//packages/botan2/2.19.5/4.fc41/aarch64/botan2-2.19.5-4.fc41.aarch64.rpm | 2.19.5 | https://botan.randombit.net/
5 | breezy | Y | 3.3.8 |  | Akarsh | Not Started | [6 empty] | 3.0.2 | 3.0.2 | 3.3.8 | breezy-3.3.8-1.fc41 ¦ Build Info ¦ koji | 3.3.8 | Tags · breezy-team/breezy · GitHub
6 | bsf | N | NA |  | Akarsh | Ongoing |  | 2024-08-10 | 2024-08-10 |  |  |  | 2.4.0 | 2.4.0 | 2.4.0 | https://kojipkgs.fedoraproject.org//packages/bsf/2.4.0/56.fc41/src/bsf-2.4.0-56.fc41.src.rpm | 2.4.0 | Apache Commons BSF™ - Bean Scripting Framework
7 | buildah | Y | 1.37.5 |  | Akarsh | Not Started | [6 empty] | 1.18.0 | 1.18.0 | 1.37.5 | https://kojipkgs.fedoraproject.org//packages/buildah/1.37.3/2.fc42/src/buildah-1.37.3-2.fc42.src.rpm | 1.37.0 | Buildah Release Announcements ¦ buildah.io
8 | bwidget | Y | 1.10.1 |  | Akarsh | PR Raised | Upgrade:bwidget to version 1.10.1 by AkarshHCL · Pull Request #11050 · microsoft/azurelinux | 2024-11-05 | 2024-11-05 | 2024-11-05 | Y | 2024-11-05 | 1.9.7 | 1.9.7 | 1.9.7 | https://kojipkgs.fedoraproject.org//packages/bwidget/1.9.7/23.fc41/src/bwidget-1.9.7-23.fc41.src.rpm | 1.10.1 | https://sourceforge.net/projects/tcllib/files/BWidget/1.10.1/
9 | cachefilesd | N | NA |  | Akarsh | NA-Uptodate | N/A | 2024-10-18 | 2024-10-18 |  | Y | 18-10-2024 | 0.10.10 | 0.10.10 | 0.10.10 | cachefilesd-0.10.10-19.fc41 ¦ Build Info ¦ koji (fedoraproject.org) | 0.10.10 | http://people.redhat.com/~dhowells/fscache/
10 | cairomm | Y | 1.18.2 |  | Akarsh | Not Started | [6 empty] | 1.12.0 | 1.12.0 | 1.14.5 | cairomm-1.14.5-5.fc41 ¦ Build Info ¦ koji (fedoraproject.org) | 1.18.2 | https://www.cairographics.org/
11 | capstone | Y | 5.0.1 |  | Akarsh | Not Started | [6 empty] | 4.0.2 | 4.0.2 | 5.0.1 | capstone-5.0.1-6.fc42 ¦ Build Info ¦ koji (fedoraproject.org) | 5.0.0 | http://www.capstone-engine.org/
12 | cassandra | N | NA |  | Akarsh | Not Started | [6 empty] | 4.0.10 | 4.0.10 | Not Available | Overview - rpms/cassandra - src.fedoraproject.org | Not Available | Overview - rpms/cassandra - src.fedoraproject.org
13 | catatonit | N | NA |  | Akarsh | NA-Uptodate | N/A | 2024-10-18 | 2024-10-18 |  | Y | 21-10-2024 | 0.1.7 | 0.1.7 | 0.1.7 | \ | 0.2.0 | https://github.com/openSUSE/catatonit
14 | cdparanoia | N | NA |  | Akarsh | NA-Uptodate | N/A | 2024-10-18 | 2024-10-18 |  | Y | 21-10-2024 | 10.2 | 10.2 | 10.2 | cdparanoia-10.2-45.fc41 ¦ Build Info ¦ koji (fedoraproject.org) | 10.2 | http://www.xiph.org/paranoia/index.html
15 | cdrdao | Y | 1.2.5 |  | Akarsh | Not Started | [6 empty] | 1.2.4 | 1.2.4 | 1.2.5 | cdrdao-1.2.5-12.fc41 ¦ Build Info ¦ koji (fedoraproject.org) | 1.2.5 | http://cdrdao.sourceforge.net/
16 | celt051 | Y | 0.11.1 |  | Akarsh | Not Started | [6 empty] | 0.5.1.3 | 0.5.1.3 | 0.5.1.3 | celt051-0.5.1.3-29.fc41 ¦ Build Info ¦ koji (fedoraproject.org) | 0.11.1 | http://www.celt-codec.org/
17 | certmonger | Y | 0.79.20 |  | Akarsh | Not Started | [6 empty] | 0.79.13 | 0.79.13 | 0.79.20 | certmonger-0.79.20-2.fc41 ¦ Build Info ¦ koji (fedoraproject.org) | 0.79.20 | http://pagure.io/certmonger/
18 | cfitsio | Y | 4.5.0 |  | Akarsh | Not Started | [6 empty] | 4.0.0 | 4.0.0 | 4.5.0 | cfitsio-4.5.0-5.fc42 ¦ Build Info ¦ koji (fedoraproject.org) | 4.5.0 | http://heasarc.gsfc.nasa.gov/fitsio/
19 | cgdcbxd | N | NA |  | Akarsh | NA-Uptodate | N/A | 2024-10-18 | 2024-10-18 |  | Y | 21-10-2024 | 1.0.2 | 1.0.2 | Orphan | Overview - rpms/cgdcbxd - src.fedoraproject.org | 1.2.0 | https://github.com/jrfastab/cgdcbxd
20 | cglib | Y | 3.3.0 |  | Akarsh | Not Started | [6 empty] | 3.2.4 | 3.2.4 | 3.3.0 | cglib-3.3.0-16.fc41 ¦ Build Info ¦ koji (fedoraproject.org) | 3.3.0 | https://github.com/cglib/cglib
21 | iso-codes | Y | 4.17.0 |  | Akarsh | PR Raised | https://github.com/microsoft/azurelinux/pull/10821 | 21-10-2024 |  | 23-10-2024 | Y | 21-10-2024 | 4.4 | 4.4 | 4.17.0 | iso-codes-4.17.0-1.fc42 ¦ Build Info ¦ koji (fedoraproject.org) | 4.17.0 | https://salsa.debian.org/iso-codes-team/iso-codes
22 | isomd5sum | Y | 1.2.5 |  | Akarsh | Not Started | [6 empty] | 1.2.3 | 1.2.3 | 1.2.5 | isomd5sum-1.2.5-2.fc41 ¦ Build Info ¦ koji (fedoraproject.org) | 1.2.5 | https://github.com/rhinstaller/isomd5sum
23 | iwd | Y | 3 |  | Akarsh | Ongoing |  |  |  | 23-10-2024 | Y | 21-10-2024 | 1.22 | 1.22 | 3 | https://koji.fedoraproject.org/koji/buildinfo?buildID=2571804 | 3 | https://git.kernel.org/pub/scm/network/wireless/iwd.git/tag/?h=3.0
24 | jabberpy | N | NA |  | Akarsh | NA-Uptodate | N/A | 14-10-2024 | 14-10-2024 |  | Y | 14-10-2024 | 0.5 | 0.5 | Orphan | Overview - rpms/jabberpy - src.fedoraproject.org | 0.5 | Jabber.py download ¦ SourceForge.net
25 | jakarta-taglibs-standard | N | NA |  | Akarsh | Ongoing | N/A |  |  |  | N | 14-10-2024 | 1.1.1 | 1.1.1 | Orphan | Overview - rpms/jakarta-taglibs-standard - src.fedoraproject.org | Deprecated | Apache Taglibs - Apache Taglibs
26 | jansi | N | NA |  | Akarsh | NA-Uptodate | N/A | 14-10-2024 | 14-10-2024 |  | Y | 14-102024 | 2.4.0 | 2.4.0 | 2.4.1 | jansi-2.4.1-4.fc41 ¦ Build Info ¦ koji (fedoraproject.org) | 2.4.0 | http://fusesource.github.io/jansi/
27 | jarjar | N | NA |  | Akarsh | NA-Uptodate | N/A | 14-10-2024 | 14-10-2024 |  | Y | 14-10-2024 | 1.4 | 1.4 | orphan | Overview - rpms/jarjar - src.fedoraproject.org | N/A | N/A | Revisit
28 | javacc | Y | 7.0.13 |  | Akarsh | Not Started |  |  |  |  | N | 14-10-2024 | 7.0.4 | 7.0.4 | 7.0.13 | javacc-7.0.13-7.fc41 ¦ Build Info ¦ koji (fedoraproject.org) | 7.0.13 | JavaCC ¦ The most popular parser generator for use with Java applications. | Unbuilt in daily build status
29 | javacc-bootstrap | Y | Revisit |  | Akarsh | Not Started |  |  |  |  | N | 14-10-2024 | 7.0.4 | 7.0.4
30 | jbigkit | N | NA |  | Akarsh | Not Started |  |  |  |  | N | 14-10-2024 | 2.1 | 2.1 | 2.1 | jbigkit-2.1-30.fc41 ¦ Build Info ¦ koji (fedoraproject.org) | 2.1 | http://www.cl.cam.ac.uk/~mgk25/jbigkit/
31 | jboss-interceptors-1.2-api | N | NA |  | Akarsh | Not Started |  |  |  |  | N | 14-10-2024 | 1 | 1 | Orphan | Overview - rpms/jboss-interceptors-1.2-api - src.fedoraproject.org | 1 | https://github.com/jboss/jboss-interceptors-api_spec
32 | jdepend | Y | 2.1 |  | Akarsh | Not Started | [6 empty] | 2.9.1 | 2.9.1 | 2.1 | jdepend-2.10-12.fc41 ¦ Build Info ¦ koji (fedoraproject.org) | 2.1 | https://github.com/clarkware/jdepend
33 | jdom2 | Y | 2.0.6.1 |  | Akarsh | PR Raised | Upgrade: jdom2 to version 2.0.6.1 by AkarshHCL · Pull Request #11049 · microsoft/azurelinux | 2024-11-11 | 2024-11-13 | 2024-11-13 | Y | 2024-11-11 | 2.0.6 | 2.0.6 | 2.0.6.1 | jdom2-2.0.6.1-9.fc41 ¦ Build Info ¦ koji (fedoraproject.org) |  | Access denied
34 | jfsutils | N | NA |  | Akarsh | NA-Uptodate | N/A | 14-10-2024 | 14-10-2024 |  | Y | 14-10-2024 | 1.1.15 | 1.1.15 | 1.1.15 | jfsutils-1.1.15-28.fc41 ¦ Build Info ¦ koji (fedoraproject.org) | 1.1.15 | Open source : JFS project Web site (sourceforge.net)
35 | jimtcl | Y | 0.82 |  | Akarsh | Not Started |  |  |  |  | Y | 2024-10-29 | 0.78 | 0.78 | 0.82 | jimtcl-0.83-1.fc42 ¦ Build Info ¦ koji (fedoraproject.org) | 0.83 | GitHub - msteveb/jimtcl: Official repository of Jim Tcl, an open-source, small footprint implementation of Tcl
36 | jlex | N | NA |  | Akarsh | Not Started | N/A | [5 empty] | 1.2.6 | 1.2.6 | Orphan | Overview - rpms/jlex - src.fedoraproject.org | 1.2.6 | JLex: A Lexical Analyzer Generator for Java(TM) (princeton.edu)
37 | jline | Y | 3.23 |  | Akarsh | Not Started | [6 empty] | 2.14.6 | 2.14.6 | 3.23 | jline-3.23.0-4.fc40 ¦ Build Info ¦ koji (fedoraproject.org)
38 | jose | Y | 14 |  | Akarsh | Not Started |  |  |  |  | N | 2024-10-29 | 10 | 10 | 14 | jose-14-2.fc41 ¦ Build Info ¦ koji (fedoraproject.org) | 14 | https://github.com/latchset/jose
39 | js-jquery | Y | 3.7.1 |  | Akarsh | PR Raised | Update: js-jquery to version 3.7.1 by AkarshHCL · Pull Request #11053 · microsoft/azurelinux | 2024-11-13 | 2024-11-13 | 2024-11-13 | Y | 2024-10-29 | 3.5.0 | 3.5.0 | 3.7.1 | js-jquery-3.7.1-4.fc41 ¦ Build Info ¦ koji (fedoraproject.org) | 3.7.1 | https://jquery.com/
40 | jsch | N | NA |  | Akarsh | Not Started | N/A | [5 empty] | 0.1.55 | 0.1.55 | 0.1.55 | jsch-0.1.55-16.fc41 ¦ Build Info ¦ koji (fedoraproject.org) | 0.1.55 | JCraft, Inc.
41 | jsoncpp | Y | 1.9.5 |  | Akarsh | PR Raised | Upgrade: jsoncpp to version 1.9.5 by AkarshHCL · Pull Request #11068 · microsoft/azurelinux | 2024-11-14 | 2024-11-14 | 2024-11-14 | Y | 2024-10-29 | 1.9.2 | 1.9.2 | 1.9.5 | jsoncpp-1.9.5-8.fc41 ¦ Build Info ¦ koji (fedoraproject.org) | 1.9.6 | GitHub - open-source-parsers/jsoncpp: A C++ library for interacting with JSON.
42 | jsoup | Y | 1.18.1 |  | Akarsh | Ongoing | [6 empty] | 1.11.1 | 1.11.1 | 1.18.1 | jsoup-1.18.1-2.fc41 ¦ Build Info ¦ koji (fedoraproject.org) | 1.18.1 | https://jsoup.org/
43 | jtidy | Revisit | Revisit |  | Akarsh | Not Started | [6 empty] | 8 | 8
44 | junitperf | N | NA |  | Akarsh | Not Started | N/A | [5 empty] | 1.9.1 | 1.9.1 | Orphan | Overview - rpms/junitperf - src.fedoraproject.org | 1.9.1 | GitHub - clarkware/junitperf: A collection of JUnit test decorators used to measure the performance and scalability of functionality contained within existing JUnit tests.
45 | jzlib | N | NA |  | Akarsh | Not Started | N/A | [5 empty] | 1.1.3 | 1.1.3 | 1.1.3 | jzlib-1.1.3-31.fc41 ¦ Build Info ¦ koji (fedoraproject.org) | 1.1.3 | JZlib - zlib in pure Java (jcraft.com)
46 | libmodulemd1 | N | NA |  | Akarsh | NA-Uptodate | N/A | N/A | N/A | 22-10-2024 | Y | 22-10-2024 | 1.8.16 | 1.8.16 | 1.8.16 | Overview - rpms/libmodulemd1 - src.fedoraproject.org | 2.15.0 | https://github.com/fedora-modularity/libmodulemd
47 | libmpcdec | Y | 1.3.0 |  | Akarsh | Ongoing |  |  |  | 22-10-2024 |  |  | 1.2.6 | 1.2.6 | 1.3.0 | libmpcdec-1.3.0^20110810svn475-2.fc42 ¦ Build Info ¦ koji
48 | libmspub | N | N/A |  | Akarsh | NA-Uptodate | N/A | 22-10-2024 | 22-10-2024 | 22-10-2024 | Y | 22-10-2024 | 0.1.4 | 0.1.4 | 0.1.4 | libmspub-0.1.4-33.fc41 ¦ Build Info ¦ koji | 0.1.4 | http://wiki.documentfoundation.org/DLP/Libraries/libmspub
49 | libmtp | Y | 1.1.19 |  | Akarsh | PR Raised | Upgarde:Libmtp to version 1.1.19 by AkarshHCL · Pull Request #11113 · microsoft/azurelinux | 2024-11-18 | 2024-11-18 | 2024-11-18 | Y | 22-10-2024 | 1.1.18 | 1.1.18 | 1.1.19 | libmtp-1.1.19-8.fc41 ¦ Build Info ¦ koji | 1.1.21 | libmtp - Browse /libmtp/1.1.21 at SourceForge.net
50 | libmusicbrainz5 | N | N/A |  | Akarsh | NA-Uptodate | N/A |  |  | 22-10-2024 | N | 2024-10-22 | 5.1.0 | 5.1.0 | 5.1.0 | libmusicbrainz5-5.1.0-25.fc41 ¦ Build Info ¦ koji
51 | libmwaw | Y | 0.3.22 |  | Akarsh | PR Raised | Upgrade:Libmwaw to version 0.3.22 by AkarshHCL · Pull Request #11138 · microsoft/azurelinux | 2024-11-18 | 2024-11-19 | 2024-11-19 | Y | 2024-10-22 | 0.3.17 | 0.3.17 | 0.3.22 | libmwaw-0.3.22-4.fc41 ¦ Build Info ¦ koji | 0.3.22 | libmwaw - Browse /libmwaw at SourceForge.net
52 | libnet | Y | 1.3 |  | Akarsh | PR Raised | https://github.com/microsoft/azurelinux/pull/11137 | 2024-11-18 | 2024-11-18 | 2024-11-18 | Y | 2024-10-22 | 1.2 | 1.2 | 1.3 | libnet-1.3-4.fc41 ¦ Build Info ¦ koji | 1.3 | GitHub - libnet/libnet: A portable framework for low-level network packet construction
53 | libntlm | N | N/A |  | Akarsh | NA-Uptodate | N/A | N/A | N/A | 22-10-2024 | Y | 2024-10-22 | 1.6 | 1.6 | 1.6 | libntlm-1.6-10.fc41 ¦ Build Info ¦ koji | 1.8 | gsasl / Libntlm · GitLab
54 | libnumbertext | Y | 1.0.11 |  | Akarsh |  |  |  |  | 22-10-2024 |  |  | 1.0.5 | 1.0.5 | 1.0.11 | libnumbertext-1.0.11-7.fc41 ¦ Build Info ¦ koji | 1.0.11 | GitHub - Numbertext/libnumbertext: Number to number name and money text conversion libraries in C++, Java, JavaScript and Python & LibreOffice Calc Extension
55 | liboauth | N | N/A |  | Akarsh | NA-Uptodate | N/A | 22-10-2024 | 22-10-2024 | 22-10-2024 | Y | 22-10-2024 | 1.0.3 | 1.0.3 | 1.0.3 | liboauth-1.0.3-24.fc41 ¦ Build Info ¦ koji | 1.0.3 | liboauth - Browse Files at SourceForge.net
56 | libodfgen | N | N/A |  | Akarsh | NA-Uptodate | N/A | 22-10-2024 | 22-10-2024 | 22-10-2024 | Y | 22-10-2024 | 0.1.8 | 0.1.8 | 0.1.8 | libodfgen-0.1.8-12.fc41 ¦ Build Info ¦ koji | 0.1.8 | WordPerfect Document importer / Wiki / libodfgen
57 | libofa | N | N/A |  | Akarsh | NA-Uptodate | N/A | 22-10-2024 | 22-10-2024 | 22-10-2024 | Y | 22-10-2024 | 0.9.3 | 0.9.3 | 0.9.3 | libofa-0.9.3-48.fc41 ¦ Build Info ¦ koji | 0.9.3 | Google Code Archive - Long-term storage for Google Code Project Hosting.
58 | libogg | Y | 1.3.5 |  | Akarsh |  |  |  |  | 22-10-2024 |  |  | 1.3.4 | 1.3.4 | 1.3.5 | libogg-1.3.5-9.fc41 ¦ Build Info ¦ koji | 1.3.5 | Ftp - /pub/xiph/releases/ogg/ :: Oregon State University Open Source Lab
59 | liboggz | N | N/A |  | Akarsh | NA-Uptodate | N/A | 2024-11-18 | 2024-11-18 | 2024-11-18 | Y | 2024-11-18 | 1.1.1 | 1.1.1 | 1.1.1 | liboggz-1.1.1-32.fc42 ¦ Build Info ¦ koji
60 | liboil | N | N/A |  | Akarsh | NA-Uptodate | N/A | 2024-11-18 | 2024-11-18 | 22-10-2024 | Y | 2024-11-18 | 0.3.16 | 0.3.16 | 0.3.16 | liboil-0.3.16-34.fc41 ¦ Build Info ¦ koji | 0.3.17 | Index of /download
61 | libomxil-bellagio | N | N/A |  | Akarsh | NA-Uptodate | N/A | 22-10-2024 | 22-10-2024 | 22-10-2024 | Y | 22-10-2024 | 0.9.3 | 0.9.3 | 0.9.3 | libomxil-bellagio-0.9.3-33.fc40 ¦ Build Info ¦ koji | 0.9.3 | http://omxil.sourceforge.net/
62 | libopenraw | N | N/A |  | Akarsh | NA-Uptodate | N/A | 2024-11-18 | 2024-11-18 | 2024-11-18 | Y | 2024-11-18 | 0.1.3 | 0.1.3 | 0.1.3 | libopenraw-0.1.3-18.fc41 ¦ Build Info ¦ koji
63 | liboping | N | N/A |  | Akarsh | NA-Uptodate | N/A | 23-10-2024 | 23-10-2024 | 23-10-2024 | Y | 23-10-2024 | 1.10.0 | 1.10.0 | 1.10.0 | Overview - rpms/liboping - src.fedoraproject.org | 1.10.0 | octo's ping library - noping
64 | libosinfo | Y | 1.11.0 |  | Akarsh |  |  |  |  | 23-10-2024 |  |  | 1.10.0 | 1.10.0 | 1.11.0 | https://koji.fedoraproject.org/koji/buildinfo?buildID=2496905 | 1.11.0 | https://gitlab.com/libosinfo/libosinfo/-/tags
65 | libotf | Y | 0.9.16 |  | Akarsh |  |  |  |  | 23-10-2024 |  |  | 0.9.13 | 0.9.13 | 0.9.16 | https://koji.fedoraproject.org/koji/buildinfo?buildID=2496907 | 0.9.16 | https://download.savannah.nongnu.org/releases/m17n/
66 | libotr | N | N/A |  | Akarsh |  |  |  |  | 23-10-2024 | N | 23-10-2024 | 4.1.1 | 4.1.1 | 4.1.1 | https://koji.fedoraproject.org/koji/buildinfo?buildID=2496908 | 4.1.1 | https://otr.cypherpunks.ca/index.php#downloads
67 | libpagemaker | N | N/A |  | Akarsh | NA-Uptodate | N/A | 23-10-2024 | 23-10-2024 | 23-10-2024 | Y | 23-10-2024 | 0.0.4 | 0.0.4 | 0.0.4 | https://koji.fedoraproject.org/koji/buildinfo?buildID=2496901 | 0.0.4 | https://dev-www.libreoffice.org/src/libpagemaker/
68 | libpaper | Y | 2.2.5 |  | Akarsh |  |  |  |  | 23-10-2024 |  |  | 1.1.28 | 1.1.28 | 2.1.1 | https://koji.fedoraproject.org/koji/buildinfo?buildID=2496916 | 2.2.5 | https://github.com/rrthomas/libpaper/releases/tag/v2.2.5
69 | libpeas | Y | 2.0.5 |  | Akarsh |  |  |  |  | 23-10-2024 |  |  | 1.26.0 | 1.26.0 | 2.0.5 | https://koji.fedoraproject.org/koji/buildinfo?buildID=2549482 | 2.0.5 | https://download.gnome.org/sources/libpeas/2.0/
70 | libpfm | Y | 4.13.0 |  | Akarsh |  |  |  |  | 23-10-2024 |  |  | 4.10.1 | 4.10.1 | 4.13.0 | https://koji.fedoraproject.org/koji/buildinfo?buildID=2496923 | 4.13.0 | https://perfmon2.sourceforge.net/